## Gantt Chart
GANTT CHART
PROJECT TITLE |  | BaskeStats |  |  |  |  | COMPANY NAME | [6 empty] | BaskeStats
PROJECT MANAGER |  | Nikolaos Papadopoulos |  |  |  |  | DATE | [6 empty] | 2023-11-01
[44 empty] | D1 | [36 empty] | D2
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception
1.1 | Requirements Gathering | Nikolaos Papadopoulos | 2023-11-01 | 2023-11-03 | 2 | 100% | bar: WEEK 1 W to WEEK 1 F; WEEK 5 R
1.2 | Research | Nikolaos Papadopoulos | 2023-11-03 | 2023-11-08 | 5 | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 5 R
1.3 | Projections | Nikolaos Papadopoulos | 2023-11-07 | 2023-11-10 | 3 | 100% | bar: WEEK 2 R to WEEK 3 T; WEEK 5 R
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Nikolaos Papadopoulos | 2023-11-10 | 2023-11-15 | 5 | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 5 R
2.2 | Program Vision | Nikolaos Papadopoulos | 2023-11-10 | 2023-11-15 | 5 | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 5 R
2.3 | Problem Statement | Nikolaos Papadopoulos | 2023-11-10 | 2023-11-15 | 5 | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 5 R
2.4 | Constraints and Limitations | Nikolaos Papadopoulos | 2023-11-12 | 2023-11-15 | 3 | 100% | bar: WEEK 3 R to WEEK 4 T; WEEK 5 R
2.5 | User Profiles and Interactions (Target Audience and Environment) | Nikolaos Papadopoulos | 2023-11-12 | 2023-11-15 | 3 | 100% | bar: WEEK 3 R to WEEK 4 T; WEEK 5 R
3 | Project Initiation
3.1 | GitHub Team and Repository Creation and Management | Fotis Arvanitidis | 2023-11-13 | 2024-01-08 | 55 | 80% | bar: WEEK 3 F to WEEK 15 T
3.2 | User Table | Aggelos Theologou | 2023-11-15 | 2023-11-20 | 5 | 100% | bar: WEEK 4 T to WEEK 5 T; WEEK 5 R
3.2.1 | Use Case Diagram | Kwnstantina Liogka | 2023-11-17 | 2023-11-22 | 5 | 100% | bar: WEEK 4 R to WEEK 5 R
3.2.2 | Use Case Specifications | Kyriakos Stergiou | 2023-11-22 | 2023-11-29 | 7 | 100% | bar: WEEK 5 R to WEEK 7 M
3.3 | Functional and non-Functional Requirements | Nikolaos Papadopoulos | 2023-11-22 | 2023-11-29 | 7 | 100% | bar: WEEK 5 R to WEEK 7 M
3.4 | Sequence (UML) Diagram | Aggelos Theologou | 2023-11-25 | 2023-12-01 | 6 | 100% | bar: WEEK 5 R; WEEK 6 T to WEEK 7 W
4 | Database Design and Management
4.1 | Database Schema Design (ER) | Kwnstantina Liogka | 2023-12-11 | 2023-12-18 | 7 | 0% | bar: WEEK 5 R; WEEK 9 W to WEEK 11 F
4.2 | Database Implementation | Kwnstantina Liogka | 2023-12-18 | 2023-12-25 | 7 | 0% | bar: WEEK 5 R; WEEK 10 F to WEEK 12 T
4.3 | Database Connectivity | Aggelos Theologou | 2023-12-23 | 2023-12-31 | 8 | 0% | bar: WEEK 5 R; WEEK 11 M to WEEK 13 W
5 | Front-end Development
5.1 | UI/UX Design | Nikolaos Papadopoulos | 2023-12-13 | 2023-12-18 | 5 | 0% | bar: WEEK 5 R; WEEK 9 F to WEEK 11 F
5.2 | Front-end Framework Selection and Integration | Fotis Arvanitidis | 2023-12-18 | 2023-12-20 | 2 | 0% | bar: WEEK 5 R; WEEK 10 F to WEEK 11 F
5.3 | Front-end Implementation | Fotis Arvanitidis | 2023-12-20 | 2024-01-01 | 11 | 0% | bar: WEEK 5 R; WEEK 11 M to WEEK 13 R
6 | Back-End Development
6.1 | Server-Side Logic Design | Kwnstantina Liogka | 2023-12-15 | 2023-12-20 | 5 | 0% | bar: WEEK 5 R; WEEK 10 T to WEEK 11 F
6.2 | Back-end Framework Selection and Integration | Kyriakos Stergiou | 2023-12-20 | 2023-12-22 | 2 | 0% | bar: WEEK 5 R
6.3 | Back-end Implementation | Kyriakos Stergiou | 2023-12-22 | 2024-01-04 | 12 | 0% | bar: WEEK 5 R; WEEK 11 M to WEEK 14 F
7 | Integration and Testing
7.1 | API Integration | Kyriakos Stergiou | 2023-12-31 | 2024-01-06 | 6 | 0% | bar: WEEK 5 R; WEEK 12 W to WEEK 14 F
7.2 | Unit and Integration Testing | Nikolaos Papadopoulos | 2023-12-18 | 2024-01-06 | 18 | 0% | bar: WEEK 5 R; WEEK 11 M to WEEK 14 F
7.3 | User Acceptance Testing (UAT) | Nikolaos Papadopoulos | 2024-01-03 | 2024-01-08 | 5 | 0% | bar: WEEK 5 R; WEEK 14 M to WEEK 14 F
7.4 | Code Refinement | Nikolaos Papadopoulos | 2024-01-03 | 2024-01-08 | 5 | 0% | bar: WEEK 5 R; WEEK 14 M to WEEK 15 M
7.5 | Deployment | Nikolaos Papadopoulos | 2024-01-03 | 2024-01-08 | 5 | 0% | bar: WEEK 5 R; WEEK 14 M to WEEK 15 T
8 | Development and Documentation
8.1 | Class Diagrams | Nikolaos Papadopoulos | 2023-12-11 | 2023-12-18 | 7 | 0% | bar: WEEK 5 R; WEEK 9 W to WEEK 11 F
8.1 | General Documentation | Nikolaos Papadopoulos | 2023-12-14 | 2024-01-08 | 24 | 0% | bar: WEEK 5 R; WEEK 9 F to WEEK 15 T
8.2 | YouTube Tutorial | Nikolaos Papadopoulos | 2024-01-08 | 2024-01-10 | 2 | 0% | bar: WEEK 5 R; WEEK 15 T to WEEK 15 R